{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["工程表"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"工程表","index":0,"n_rows":30,"n_cols":93,"rows_kept":30,"cut":false,"hidden":false,"merged":[[9,38,9,52],[11,38,11,52],[11,10,11,21],[11,74,11,86],[20,66,20,70],[15,74,15,86],[17,74,17,86],[19,74,19,86],[7,66,7,70],[9,66,9,70],[11,66,11,70],[7,74,7,86],[9,74,9,86],[15,66,15,70],[17,66,17,70],[19,66,19,70],[16,66,16,70],[18,66,18,70],[25,80,25,86],[19,31,19,35],[19,38,19,42],[23,66,23,70],[23,31,23,35],[19,45,19,49],[25,10,25,21],[24,17,24,21],[24,10,24,16],[29,6,29,16],[19,10,19,21],[23,10,23,19],[29,17,29,86],[25,31,25,35],[23,38,23,42],[25,38,25,42],[23,45,23,49],[25,45,25,49],[25,66,25,70],[23,74,23,77],[25,74,25,77],[23,80,23,86],[15,10,15,21],[9,10,9,21],[8,10,8,21],[17,10,17,21],[4,31,4,60],[5,55,5,56],[15,31,15,35],[17,31,17,35],[15,38,15,49],[17,38,17,49],[16,17,16,21],[7,10,7,21],[7,31,7,35],[9,31,9,35],[11,31,11,35],[7,38,7,52],[3,32,3,37],[1,32,2,37],[0,32,0,37],[4,62,4,91],[5,66,5,67],[5,86,5,87],[5,35,5,36],[5,58,5,60],[0,38,0,41],[0,42,0,45],[2,42,3,45],[2,38,3,41],[1,38,1,41],[1,42,1,45],[0,1,2,17],[3,24,3,26],[3,27,3,29],[5,5,5,6],[5,25,5,26],[0,18,2,23],[0,24,0,26],[1,24,2,26],[0,27,0,29],[1,27,2,29],[4,1,4,30],[3,30,3,31],[1,30,2,31],[0,30,0,31]]}
["*黄色:休日　","MIRS1401班",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"工　程　表",null,null,null,null,null,"眞野千輝",null,null,"リーダー,ソフト",null,null,"尾関主馬",null,"エレキ",null,null,null,null,null,"伊藤喬章",null,null,null,"メカ"]
[" 青色:終了過程",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"五十嵐雄介",null,null,"プロジェクト兼任,ソフト",null,null,"佐野友里花",null,"メカ",null,null,null,null,null,"渡邉武大",null,null,null,"メカ"]
[" ",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"高井悠",null,null,null,"エレキ"]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"西留直人",null,null,"ドキュメントマネージャ",null,null,"宇佐美昴礼",null,"エレキ"]
["平成26年11月","11月",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"12月",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"1月"]
["担当者",1,null,null,null,null,null,null,null,null,10,null,null,null,null,null,null,null,null,null,20,null,null,null,null,"テスト",null,null,null,null,30,1,null,null,null,null,null,null,null,null,10,null,null,null,null,null,null,null,null,null,20,null,null,null,null,null,null,null,"冬休み",null,null,31,1,null,null,null,null,null,null,null,null,10,null,null,null,null,null,null,null,null,null,20,null,null,null,null,"本番",null,null,null,null,null,31]
["エレキ"]
["宇佐美昴礼",null,null,null,null,null,null,null,null,null,"モーター制御ボード 試験",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"ドータボード制作・試験",null,null,null,null,null,null,"FPGAボード制作・試験",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"FPGAボード制作・試験",null,null,null,null,null,null,null,"エンターテイメント性の向上&故障への対応"]
[null,null,null,null,null,null,null,null,null,null,"エレキ詳細設計書制作"]
["高井悠",null,null,null,null,null,null,null,null,null,"エレキ詳細設計書制作",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"ドータボード制作・試験",null,null,null,null,null,null,"FPGAボード制作・試験",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"FPGAボード制作・試験",null,null,null,null,null,null,null,"エンターテイメント性の向上&故障への対応"]
[]
["尾関主馬",null,null,null,null,null,null,null,null,null,"FPGAの理解",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"FPGAボード制作・試験",null,null,null,null,null,null,"FPGAボード制作・試験",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"FPGAボード制作・試験",null,null,null,null,null,null,null,"エンターテイメント性の向上&故障への対応"]
[]
[]
["メカ"]
["渡邉武大",null,null,null,null,null,null,null,null,null,"メカ詳細設計書制作",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"シャーシの作成",null,null,null,null,null,null,"針の突出機構の作成",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"針の突出機構の作成",null,null,null,null,null,null,null,"エンターテイメント性の向上&故障への対応"]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"オムニホイールの試験",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"組み立て"]
["伊藤喬章",null,null,null,null,null,null,null,null,null,"メカ詳細設計書制作",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"バンパーの作成",null,null,null,null,null,null,"針の突出機構の作成",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"針の突出機構の作成",null,null,null,null,null,null,null,"エンターテイメント性の向上&故障への対応"]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"組み立て"]
["佐野友里花",null,null,null,null,null,null,null,null,null,"メカ詳細設計書制作",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"その他の部品の作成",null,null,null,null,null,null,"補助",null,null,null,null,null,null,"針の突出機構の作成",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"針の突出機構の作成",null,null,null,null,null,null,null,"エンターテイメント性の向上&故障への対応"]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"組み立て"]
[]
["ソフト"]
["眞野千輝",null,null,null,null,null,null,null,null,null,"モーター制御ボード 試験",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"標準プログラム(修正)",null,null,null,null,null,null,"地図プログラム",null,null,null,null,null,null,"画像処理プログラム",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"巡回用プログラム",null,null,null,null,null,null,null,"追跡用プログラム",null,null,null,null,null,"統合試験"]
[null,null,null,null,null,null,null,null,null,null,"システム基本設計書制作",null,null,null,null,null,null,"ソフト詳細設計書制作"]
["五十嵐雄介",null,null,null,null,null,null,null,null,null,"ソフト詳細設計書制作",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"標準プログラム(修正)",null,null,null,null,null,null,"地図プログラム",null,null,null,null,null,null,"画像処理プログラム",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"巡回用プログラム",null,null,null,null,null,null,null,"追跡用プログラム",null,null,null,null,null,"統合試験"]
[]
[]
["ドキュメントマネージャー"]
["西留直人",null,null,null,null,null,"システム基本設計書制作",null,null,null,null,null,null,null,null,null,null,"ドキュメント管理、スケジュール管理、マネジメント、補欠要員"]